## Sheet1
Product Backlog - Neuro-Symbolic Patient Knowledge Graph (N-PKG)
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days) | start date | end date
1 | Live Audio Transcription | Data Ingestion | As a doctor, I want to speak clinical notes into the system so that they are automatically transcribed without manual typing. | Must | Done | 1. System records audio from microphone in real time. 2. Whisper model transcribes speech to text accurately. 3. Transcription is saved and passed to the NLP pipeline. | Integrate OpenAI Whisper base model.- Record audio using sounddevice library.- Save transcript to a text variable for downstream processing. | Transcription latency should be under 30 seconds for a 20-second recording.- System should handle medical terminology with reasonable accuracy. | 3 days | 3 days | 2026-02-01 | 2026-02-04
2 | Medical Entity Extraction | NLP Pipeline | As a developer, I want the system to identify medical terms in transcribed text so that diseases, medications, and symptoms are automatically detected. | Must | Done | 1. scispaCy model loads and processes clinical text. 2. Medical entities such as diseases, drugs, and symptoms are extracted. 3. Output is a structured list of entity objects with text and label. | Load en_core_sci_sm scispaCy model.- Run NLP pipeline on input transcript.- Return list of detected entities with labels. | Entity extraction should complete in under 5 seconds per note.- Model must correctly identify at least core clinical terms like drug names and diseases. | 3 days | 3 days | 2026-02-07 | 2026-02-11
3 | Clinical Data Structuring with BioMistral | NLP Pipeline | As a developer, I want BioMistral to organise extracted entities into a structured JSON so that patient data is consistently formatted for storage. | Must | Done | 1. BioMistral receives transcript and raw entities. 2. Returns valid JSON with patient name, age, gender, diseases, medications, allergies, dates, and warnings. 3. JSON parser strips extra text and validates output. | Integrate BioMistral 7B via langchain-ollama.- Design prompt with [INST] tags for structured JSON output.- Parse and clean JSON response. | BioMistral response time should be under 60 seconds.- Output must be valid parsable JSON 90% of the time.- Temperature set to 0.0 for deterministic output. | 5 days | 5 days | 2026-02-15 | 2026-02-20
4 | Neo4j Knowledge Graph Storage | Knowledge Graph | As a developer, I want patient data stored in a Neo4j graph so that relationships between patients, diseases, medications, and allergies are queryable. | Must | In Progress | 1. Patient node is created or updated in Neo4j. 2. Disease, Medication, Allergy, and Date nodes are linked with correct relationships. 3. Data can be retrieved and verified from the graph. | Connect to Neo4j using bolt protocol.- Create nodes for Patient, Disease, Medication, Allergy, Date, Warning.- Create relationships HAS_CONDITION, PRESCRIBED, ALLERGIC_TO, HAS_APPOINTMENT, HAS_WARNING. | Graph write operations should complete in under 3 seconds per patient.- All relationships must be correctly formed and queryable. | 5 days |  | 2026-02-25 | 2026-03-02
5 | Symbolic Rule Engine | Safety Validation | As a doctor, I want the system to automatically flag dangerous drug-disease combinations so that unsafe prescriptions are blocked before they reach the patient. | Must | Backlog | 1. Rule engine checks prescribed medications against patient conditions. 2. Conflict is detected and an alert is raised for known contraindications. 3. Safe prescriptions are approved and passed to the output layer. | Define at least 15 medical safety rules in Python.- Query Neo4j graph for patient history before approving prescription.- Return CONFLICT or APPROVED status with reason. | Rule engine must check all defined rules in under 2 seconds.- Zero false negatives for defined contraindication rules. | 5 days |  | 2026-03-05 | 2026-03-10
6 | Doctor Interface | User Interface | As a doctor, I want to input patient information and receive validated prescription suggestions so that I can make safe and informed clinical decisions. | Must | Backlog | 1. Doctor can enter or speak patient notes. 2. System returns a validated prescription suggestion. 3. Conflicts are clearly flagged with reason. | Build Streamlit UI for doctor input.- Display approved or blocked status with rule details.- Show extracted patient data alongside suggestion. | UI should load in under 3 seconds.- All validation results must be clearly visible without scrolling. | 5 days |  | 2026-03-12 | 2026-03-17
7 | Patient Summary Generation | User Interface | As a patient, I want a simple summary of my prescription with key dates and warnings highlighted so that I can understand my treatment plan clearly. | Must | Backlog | 1. System generates a plain language summary of the approved prescription. 2. Medications, warnings, and important dates are clearly highlighted. 3. Summary is displayed in a readable format in the patient interface. | Prompt BioMistral to rewrite prescription in simple language.- Extract and highlight medications, dates, and warnings using LangChain output parser.- Display in Streamlit patient view. | Summary generation should complete in under 60 seconds.- All critical warnings must appear prominently. | 4 days |  | 2026-03-19 | 2026-03-24
8 | Full Pipeline Integration | Integration | As a developer, I want all pipeline stages connected end to end so that audio input flows automatically through to patient summary output. | Must | Backlog | 1. Audio input flows through Whisper, scispaCy, BioMistral, Neo4j, Rule Engine, and Patient Summary without manual intervention. 2. All 15 synthetic patients are processed successfully. 3. System correctly catches at least one conflict in test data. | Connect pipeline.py to integrate all modules.- Test with all 15 synthetic patient notes.- Verify conflict detection with deliberately bad test data. | Full pipeline for one patient should complete in under 3 minutes.- Error handling must prevent crashes on malformed input. | 5 days |  | 2026-03-26 | 2026-04-01
9 | Synthetic Patient Dataset | Data | As a developer, I want 15 realistic synthetic patient notes so that the system can be tested without using real patient data. | Must | Done | 1. 15 patient notes are created covering diverse conditions and medications. 2. Notes include diseases, medications, allergies, symptoms, dates, and warnings. 3. At least 3 notes contain deliberate drug-disease conflicts for rule engine testing. | Manually create 15 patient profiles in patient_notes.py.- Include conflict cases for Kidney Disease + NSAIDs, Liver Disease + Metformin, Warfarin + Aspirin. | All notes must be medically plausible.- Dataset must cover at least 8 different disease categories. | 2 days | 2 days | 2026-02-21 | 2026-02-23
10 | System Testing and Validation | Testing | As a developer, I want to validate the system output against expected results so that accuracy and safety of the pipeline can be demonstrated. | Should | Backlog | 1. Each patient note produces correctly structured JSON. 2. Neo4j graph contains all expected nodes and relationships. 3. Rule engine correctly identifies all planted conflicts. 4. Patient summary is readable and contains all key information. | Write test cases for each pipeline stage.- Compare BioMistral output against manually verified ground truth.- Document accuracy metrics. | System should achieve at least 85% entity extraction accuracy on test dataset.- All planted conflicts must be detected with 100% recall. | 3 days |  | 2026-04-03 | 2026-04-06