## Sheet1
Release Plan / Roadmap — Neuro-Symbolic Patient Knowledge Graph (N-PKG)
Team: Shishir Mishra (RA2311047010171) ¦ Lakshita Sreenivas (RA2311047010138) ¦ Supervisor: Dr. S Amudha
# | Release | Sprint | Start Date | End Date | Features / User Stories | Deliverable | Owner | Priority | Status | Acceptance Criteria | Notes
1 | Release 1 Environment & Data Setup | Sprint 1 | Week 1 | Week 2 | Set up Python 3.11 venv Install LangChain, Neo4j, scispaCy, Whisper Create 15 synthetic patient notes | Working dev environment 15 patient notes file | Both | Must | Done | All libraries import without errors Neo4j connects successfully Patient notes file runs and prints 15 records | Completed ahead of schedule
2 | Release 1 Environment & Data Setup | Sprint 1 | Week 1 | Week 2 | Configure .env for Neo4j credentials Test Neo4j bolt connection from Python | test_neo4j.py passing | Lakshita | Must | Done | python test_neo4j.py prints SUCCESS: Connected! | Password reset required during setup
3 | Release 2 Audio & NLP Pipeline | Sprint 2 | Week 3 | Week 4 | Integrate OpenAI Whisper base model Implement live microphone recording Transcribe doctor speech to text in real time | live_audio.py working | Shishir | Must | Done | System records and transcribes 20-second audio Transcript saved to latest_transcript.txt | FP16 warning on CPU is harmless — ignored
4 | Release 2 Audio & NLP Pipeline | Sprint 2 | Week 3 | Week 4 | Load scispaCy en_core_sci_sm model Extract medical entities from transcript Output labelled entity list | extract_entities.py working | Lakshita | Must | Done | scispaCy identifies diseases, drugs, symptoms from sample note Returns list of entity dicts | FutureWarning from spaCy is cosmetic only
5 | Release 3 BioMistral Integration | Sprint 3 | Week 5 | Week 6 | Pull and configure BioMistral 7B via Ollama Design structured JSON extraction prompt Parse and clean LLM output | structure_with_llm.py returning clean JSON | Shishir | Must | Done | BioMistral returns valid JSON with all 9 fields parse_llm_output strips extra text successfully | Used temperature=0.0 and format=json for deterministic output
6 | Release 3 BioMistral Integration | Sprint 3 | Week 5 | Week 6 | Connect full Stage 1→2→3 pipeline Test end-to-end: audio → entities → JSON Validate output for 3 sample patients | pipeline.py running Stages 1-3 | Both | Must | In Progress | Audio input produces correct JSON for 3 test patients No crashes on valid input | Stage 1-2-3 individually done; integration pending
7 | Release 4 Knowledge Graph Storage | Sprint 4 | Week 5 | Week 6 | Design Neo4j graph schema Create Patient, Disease, Medication, Allergy, Date nodes Store BioMistral JSON output in graph | neo4j_handler.py storing and retrieving patients | Lakshita | Must | In Progress | All 15 patients stored in Neo4j MATCH (n) RETURN n shows correct graph structure | Auth error resolved; storage logic ready for testing
8 | Release 4 Knowledge Graph Storage | Sprint 4 | Week 7 | Week 8 | Implement GraphRAG query layer Retrieve patient history from graph Detect conflicts with historical allergy/disease data | Graph query functions working | Both | Must | Backlog | System correctly retrieves prior conditions for a patient Conflict with historical allergy flagged in query | Depends on neo4j_handler completion
9 | Release 5 Symbolic Rule Engine | Sprint 5 | Week 7 | Week 8 | Define 15 medical safety rules in Python Check prescriptions against patient graph Return CONFLICT or APPROVED with reason | rule_engine.py blocking contraindications | Shishir | Must | Backlog | Kidney Disease + Ibuprofen flagged as CONFLICT Liver Disease + Metformin flagged as CONFLICT Safe prescription returns APPROVED | Rules based on standard clinical contraindication guidelines
10 | Release 5 Symbolic Rule Engine | Sprint 5 | Week 7 | Week 8 | Integrate rule engine into main pipeline Test with planted conflict cases in synthetic data Document all 15 rules | Rule engine integrated and tested | Both | Must | Backlog | 100% detection rate on planted conflicts Zero false positives on safe prescriptions | At least 3 synthetic patients contain deliberate conflicts
11 | Release 6 Doctor Interface | Sprint 6 | Week 9 | Week 10 | Build Streamlit doctor UI Display validated prescription suggestion Show CONFLICT alerts with reason | Doctor Streamlit interface | Lakshita | Must | Backlog | Doctor can enter/speak note and receive validated output Conflict alerts clearly visible in red Approved prescriptions shown in green | Use Streamlit for rapid prototype
12 | Release 6 Doctor Interface | Sprint 6 | Week 9 | Week 10 | Build patient summary generation Highlight medications, warnings, important dates Display in patient-friendly Streamlit view | Patient summary interface | Shishir | Must | Backlog | Summary written in plain language Medications, dates, warnings clearly highlighted Summary generated in under 60 seconds | No Teach-Back or Urgency Matrix — scope simplified
13 | Release 7 Full Integration & Testing | Sprint 7 | Week 9 | Week 10 | Connect all pipeline stages end-to-end Process all 15 synthetic patients Verify conflict detection and summaries | Fully integrated prototype | Both | Must | Backlog | All 15 patients processed without crashes All planted conflicts detected Patient summaries generated for all cases | Final demo-ready prototype
14 | Release 7 Full Integration & Testing | Sprint 7 | Week 10 | Week 10 | Record demo video Update paper to reflect actual built system Prepare Agile board final status | Demo video + updated paper | Both | Should | Backlog | Demo video under 5 minutes showing full pipeline Paper abstract updated with actual results | Present as proof-of-concept prototype
Status Legend: |  |  | Done | In Progress | Backlog